## Sheet1
Date | Hours | Description
2013-10-08 | 3.5 | Set up project, set up git repo, created Map and Tile scripts.
2013-10-09 | 2 | Continued working on Map script, generating maps with fixed sizes implemented.
2013-10-10 | 4 | Created MapCreationDialog script, removed Tile script, tiles are now just game objects with a texture.
2013-10-12 | 6 | Started MapEditor script, users can toggle-lock all tile objects in the scene hierarchy so they cannot be edited (can still multi-select them)
2013-10-13 | 4 | Users can drag/drop textures from the asset browser into the MapEditor script.
2013-10-14 | 5 | Can drag textures from the MapEditor onto map tiles.
2013-10-15 | 4 | Began reimplementing the mapEditor control into a custom inspector
2013-10-16 | 3 | Continued reimplementing the mapedtior as a custom inspector-- displays textures, painting tiles is implemented.
Total: | 31.5