## Sheet1
Date | Hours | Description
2013-10-08 | 3.5 | Set up project, set up git repo, created Map and Tile scripts.
2013-10-09 | 2 | Continued working on Map script, generating maps with fixed sizes implemented.
2013-10-10 | 4 | Created MapCreationDialog script, removed Tile script, tiles are now just game objects with a texture.
2013-10-12 | 6 | Started MapEditor script, users can toggle-lock all tile objects in the scene hierarchy so they cannot be edited (can still multi-select them)
2013-10-13 | 4 | Users can drag/drop textures from the asset browser into the MapEditor script.
2013-10-14 | 5 | Can drag textures from the MapEditor onto map tiles.
2013-10-15 | 4 | Began reimplementing the mapEditor control into a custom inspector
2013-10-16 | 3 | Continued reimplementing the mapedtior as a custom inspector-- displays textures, painting tiles is implemented.
2013-10-19 | 5 | Research spike into NavMesh (built-in unity pathing solution). Unusable for this project, cannot change tile pathing from scripts.
2013-10-20 | 7 | Finish reworking map inspector. Set up map inspector to be much more expansion-friendly (easy to expand)
2013-10-21 | 5 | Implemented Goal-Based path generation. Began coding an object to follow path.
2013-10-25 | 9 | Continued working on pathing. Finished a goal-based system, but it's too slow on larger maps (20x20+). Working on A* now, will try and combine
2013-10-26 | 7 | A* Pathing partially implemented. Takes too long to generate paths, needs some optimizing.
2013-10-27 | 13 | A* pathing completely implemented. There are a few areas that could be profiled/fixed, but it's working.
2013-10-28 | 3 | A* pathing now dynamically regenerates the path when the map is changed.
Total: | 80.5